## rAPPORTAOUT
RAPPORT MENSUEL D'ACTIVITE - CARAPACE ACCROPODE™
| A l'attention de Mr: |  | J,B,LESCHI
Chantier: | PORT BEKALTA |  | Numéro d'affaire |  | Responsable: | J,B,LESCHI
Entreprise | SOMATRA -GET |  |  |  | Responsable: | R,SASSI
Transmis à l'Entreprise le : |  |  |  | A remettre avant le:
Rapport du mois de |  | AOUT
FABRICATION
Progression |  |  | TAILLE | 1,5m3 | 2m3
Nombre de blocs fabriqués depuis le début |  |  |  | 888 | 348
Nombre de blocs fabriqués le mois précédent |  |  |  | 68 | 50
Densité moyenne du Béton
Nombre de blocs pesés
Poids moyen
Résultats d'essais de résistance du béton à la compression et à la traction: |  |  |  |  | Moyenne | Minimum
Résultats d'essais de résistance à la compression:
Résultats d'essais de résistance à la traction:
Les résultats des tests sont-ils fournis avec cette feuille:
Le planning réactualisé est-il fourni avec cette feuille:
Les défauts sont-ils maitrisés:
Types de défauts et importance ( quantité, intensité):
Autres problèmes rencontrés:
EVOLUTION GENERALE DU PROJET
[5 empty] | Partie 1 | Partie 2
Longueur de digue réalisée depuis le début ( de PM à PM): |  |  |  |  | 75ml | 145ml
Longueur de sous couche réalisée depuis le début (de PM à PM): |  |  |  |  | 75ml | 145ml
La conception de la digue doit 'il évoluer? |  |  |  |  | non | non
Les profils en travers de sous couche sont'ils transmmis avec ce document?
Y a-t-il des problèmes avec la sous couche, ou avec la butée de pied? | [5 empty] | non
Difficultés en approvisionnement régularité à contrôler? | [5 empty] | non
EVOLUTION DES LA POSE DES BLOCS
|  |  | TAILLE | 1,5m3 |  | 2m3
Nombre de blocs posés : |  |  |  | 615unités
Localisation des blocs posés (PM à PM): |  |  |  | PO1N----->P10N+PO1S----->PO6S |  | PO9N---->P013N + 9U PO7S
Contrôle de densité en pourcentages: |  |  |  | 100% |  | 100%
Les règles de pose posent t'elles des problèmes pour l'application?
non
[5 empty] | Oui | Oui
Des photos de la carapaces sont jointes à cette feuille:
ASSISTANCE CLI
Documents demandés à CLI:
Assistance particulière demandée à CLI:
Contact: |  |  | Tel: | 00216 95 615 822
Email: | hsassih@yahoo.fr |  | Fax:

## Feuil2
| Attention to | M CLOITRE
Site: | PORT EST (REUNION) | Number | 1710140 | CLI Rep. | LESCHI Jean-Bernard
Contractor : | SBTPC |  |  | Contractor Rep. | M. CLOITRE
Sent to the contractor on: |  |  | Return before:
Month of this report
MONTHLY REPORT
FABRICATION
12m3
Number of blocks fabricated since the begining
Number of blocks fabricated during the last month:
Average concrete specific weight :
Number of blocks weighted:
Average weight:
Compressive and tensile strenght
The results of tests are here attached: |  |  |  | YES | NO
The updated planning is here attached: |  |  |  | YES | NO
The defaults are over: |  |  |  | YES | NO
Types of defaults: |  |  |  | occurently | systematic
Encountered problems:
General evolution of the project
|  |  |  | Part 1 | Part 2
Breakwater core lenght ( PM to PM):
Length of filter layer built: ( From PM to PM)
The design of the breakwater has to be modified? |  |  |  | YES | NO
The surveys of the underlayer are here attached |  |  |  |  | YES | NO
Are there some problems with the underlayer or with the toe mount?
( grading of the blocks, block placement)
Placing of the CORE LOC™ units
12m3
Quantity of blocks laid in the slope:
Location of the blocks laid:( from PM to PM)
Checking of the packing density
Are the ten placing rules respected?
Witch rules are not respected?
Pictures of the armouring are here attached with this document? |  |  |  | YES | NON
CLI Technical Assistance
Documents requested by the contractor:
Spécific assitance requested by the contractor:
Documents asked by CLI to the contractor: Results of the underlayer surveys, pictures, design information
Contact: LESCHI Jean-Bernard |  | Tel: | 0033+4 76 33 43 16
Email: | jean.bernard.leschi@sogreah.fr | Fax: | 0033+4 76 33 43 33 |  | Mobile: 0033+6 07 26 47 07

## planning
PLANNING DE COULAGE ACCROPODES™
MàJ 01/12/2006
Date |  |  | Blocs / semaine | cumulé
(3U / jour)
2006 | oct | Sem 41 | 10 | 10
|  | Sem 42 | 15 | 25
|  | Sem 43 | 15 | 40
|  | Sem 44 | 12 | 52
| nov | Sem 45 | 9 | 61
|  | Sem 46 | 15 | 76
|  | Sem 47 | 15 | 91
|  | Sem 48 | 15 | 106
| dec | Sem 49 | 15 | 121
|  | Sem 50 | 15 | 136
|  | Sem 51 | 3 | 139
|  | Sem 52 | 0 | 139
2007 | jan | Sem 01 | 9 | 148
|  | Sem 02 | 15 | 163
|  | Sem 03 | 15 | 178
|  | Sem 04 | 15 | 193
|  | Sem 05 | 15 | 208
| fev | Sem 06 | 15 | 223
|  | Sem 07 | 15 | 238
PLANNING DE POSE ACCROPODES™
|  | A préciser | En cours